## Sheet1
PRODUCT BACKLOG
STORY NO. | USER STORY | PRIORITY | THEME | EFFORT ESTIMATION
1 | As a user with permission to a particular file, I want access to contribution data through a web based application | 1 | Platform | XS
2 | As a developer, I need to be able to connect to Google Drive API | 1 | Data retrieval from Drive using Drive API | M
3 | As a developer, I need to use the OAuth 2.0 protocol to authenticate users | 1 | Authentication/Log in | S
4 | As a developer, I need to be able to use the API to get the ID of a change | 2 | Data retrieval from Drive using Drive API | M
5 | As a developer, I need to be able to use the API to get the time of change | 3 | Data retrieval from Drive using Drive API | M
6 | As a developer, I need to be able to use the API to get the name of the user who made the change | 4 | Data retrieval from Drive using Drive API | M
7 | As a developer, I need to be able to retrieve the changes that a user has made to a file | 5 | Data retrieval from Drive using Drive API | XL
8 | As a user, I need to see changes to a file in chronological order in the form of a timeline provided I have permission to access that file | 5 | Interface | M
9 | As a user, I want to access the app through google authentication so that I can access my drive's files | 6 | Authentication/Log In | M
10 | As a user with many team drives, I want to select what team drive to display data, for so my screen does not get clogged up | 6 | Interface | M
11 | As a user with permission to a particular file, I want to see the contributions towards that file in the form of a pie chart | 7 | Representation of contribution/Interface | M
12 | As a user, I want to be able to see the actions taken by other users part of that Drive folder so as to know which actions they have contributed | 8 | Action used to make changes | XL
13 | As a user, I want the interface to look neat and clean so that I can look at and understand the contents with ease | 9 | Interface | L