## Sheet1
SPRINT BACKLOG
STORY NO. | USER STORY | PRIORITY | THEME | INITIAL ESTIMATION OF EFFORT | ASSIGNMENT
1 | As a user, I need to be able to see the revision information on a webpage | 1 | Printing data on the webpage | XL | Vibhas Kamal, Isara(Tito) Arunanondchai
2 | As a user, I need to be able to see what action a person has taken (such as create, delete) | 1 | Data classification | M | Mike(Quang Nghiep Ly), Isara(Tito) Arunanondchai
3 | As a user, I need to be able to see the revision data being represented in the form of a pie chart | 2 | Graphical Representation | M | Jack Beard, Manvendra Singh
4 | As a user, I need to be able to see the action data being represented in the form of a histogram | 2 | Graphical Representation | M | Jack Beard, Manvendra Singh
5 | As a user, I need to be able to see the revision data for files within a team drive even when a folder exists in said drive | 2 | Data retrieval from Drive using Drive API | M | Mike(Quang Nghiep Ly), Isara(Tito) Arunanondchai
Tasks for User Story 5 | Task 1: As a developer, I need to be able to retrieve the files inside a folder | 2 | Data retrieval from Drive using Drive API | M
| Task 2: As a developer, I need to be able to retrieve the number of actions that a user has made to a file | 3 | Data retrieval from Drive using Drive API | M
Estimated Velocity: L