## Sheet1
TEAM MEMBER | DATE | START TIME | END TIME | DESCRIPTION OF TASK
Vibhas Kamal | 2018-08-26 | 11:30 P.M. | 12:10 A.M. | Figuring out how the REST API works, how it can be applied to the project and how to create a local server using Node.js
Vibhas Kamal | 2018-08-28 | 1 P.M. | 1:22 P.M. | Team meeting regarding Product Backlog, Sprint Backlog and the allocation of tasks
Vibhas Kamal | 2018-08-28 | 8:24 P.M. | 8:54 P.M. | Completed the Product Backlog
Vibhas Kamal | 2018-08-28 | 13:00 P.M | 13:30 P.M | Team meeting - Initial process discussion
Quang Ly | 2018-08-28 | 13:00 P.M | 13:30 P.M | Team meeting - Initial process discussion
Isara Arunanondchai | 2018-08-28 | 13:00 P.M | 13:30 P.M | Team meeting - Initial process discussion
Jack Beard | 2018-08-29 | 10:00 A.M | 12:00 P.M | Team meeting - worked on product backlog
VIbhas Kamal | 2018-08-29 | 10:30 A.M. | 12:44 P.M. | Team meeting - Revising Product Backlog, Drive API
Manvendra Singh | 2018-08-29 | 11:00 A.M. | 4:00 P.M. | Team meeting - worked on product backlog and understanding and working on the api
Isara Arunanondchai | 2018-08-29 | 10:15 A.M | 12:00 P.M | Team meeting - worked on product backlog
VIbhas Kamal | 2018-08-29 | 8:40 P.M. | 11 P.M. | Working on creating a terminal Python appliction to get the changes/names/id/files in Drive
Quang Ly | 2018-08-29 | 8:40 P.M. | 11 P.M. | Working on creating a terminal Python appliction to get the changes/names/id/files in Drive
Quang Ly | 2018-08-29 | 11:45 P.M. | 1:00 A.M. | Print out all revisions of all files in user's drive in formatted output
Quang Ly | 2018-08-30 | 7:00 P.M. | 11:00 P.M. | Show the last modifying user of revisions as well as only including team drive files in the scope
Quang Ly | 2018-08-31 | 12:00 A.M | 2:00 A.M. | Formats the printing output onto the console
Jack Beard | 2018-08-31 | 4:00 P.M | 7 P.M. | Worked on product and sprint backlogs
Isara Arunanondchai | 2018-08-31 | 4.00 P.M | 7 P.M. | Worked on product and sprint backlogs
Vibhas Kamal | 2018-08-31 | 4.00 P.M | 7 P.M. | Worked on product and sprint backlogs
Vibhas Kamal | 2018-08-31 | 11:37 P.M. | 12:56 A.M. | Made changes to the Product Backlog, Sprint Backlog and updated the Project Inception document to better reflect the team's practices
Quang Ly | 2018-09-01 | 17:30 P.M. | 18:00 P.M. | Consulted the Product Owner and added new user stories into the Product Backlog
Vibhas Kamal | 2018-09-01 | 17:30 P.M. | 18:00 P.M. | Added new user stories into the Product Backlog
Isara Arunanondchai | 2018-09-06 | 12:00 P.M. | 13:00 P.M. | Worked on understanding the listing functionality to retreive changes.
Isara Arunanondchai | 2018-09-06 | 13:00 PM | 14:30 PM | Worked with retrieving changes between each revision within the code. Work in progress.
Quang Ly | 2018-09-06 | 9:00 P.M. | 11:00 P.M. | Refactored the main program by splitting it into multiple functions as well as adding comments
Jack Beard | 2018-09-07 | 5.40 P.M | 6:10 P.M | Created templates for sprint review and retrospective
Quang Ly | 2018-09-07 | 6:00 P.M. | 9:00 P.M. | Work on sprint review and sprint retrospective documents
Isara Arunanondchai | 2018-09-07 | 5:40 P.M. | 7:30 P.M. | Collaborated on sprint review and sprint retrospective.
Manvendra Singh | 2018-09-07 | 4:00 P.M. | 9:00 P.M. | Worked on sprint review and sprint retrospectives
Jack Beard | 2018-09-07 | 6:10 P.M | 7:00 P.M | Added content to both sprint review and sprint retrospective documents
Manvendra Singh | 2018-09-07 | 10:29 P.M. | 11:08 P.M. | Created a user guide for the examiner in the file README.md
Vibhas Kamal | 2018-09-07 | 4:00 P.M. | 9:00 P.M. | Sprint review, discussion regarding the Project Inception, Sprint Retrospective
END OF SPRINT 1