## Sheet1
TEAM MEMBER | DATE | START TIME | END TIME | DESCRIPTION OF TASK
Vibhas Kamal | 2018-08-26 | 11:30 P.M. | 12:10 A.M. | Figuring out how the REST API works, how it can be applied to the project and how to create a local server using Node.js
Vibhas Kamal | 2018-08-28 | 1 P.M. | 1:22 P.M. | Team meeting regarding Product Backlog, Sprint Backlog and the allocation of tasks
Vibhas Kamal | 2018-08-28 | 8:24 P.M. | 8:54 P.M. | Completed the Product Backlog
Vibhas Kamal | 2018-08-28 | 13:00 P.M | 13:30 P.M | Team meeting - Initial process discussion
Quang Ly | 2018-08-28 | 13:00 P.M | 13:30 P.M | Team meeting - Initial process discussion
Isara Arunanondchai | 2018-08-28 | 13:00 P.M | 13:30 P.M | Team meeting - Initial process discussion
Jack Beard | 2018-08-29 | 10:00 A.M | 12:00 P.M | Team meeting - worked on product backlog
VIbhas Kamal | 2018-08-29 | 10:30 A.M. | 12:44 P.M. | Team meeting - Revising Product Backlog, Drive API
Manvendra Singh | 2018-08-29 | 11:00 A.M. | 4:00 P.M. | Team meeting - worked on product backlog and understanding and working on the api
Isara Arunanondchai | 2018-08-29 | 10:15 A.M | 12:00 P.M | Team meeting - worked on product backlog
VIbhas Kamal | 2018-08-29 | 8:40 P.M. | 11 P.M. | Working on creating a terminal Python appliction to get the changes/names/id/files in Drive
Quang Ly | 2018-08-29 | 8:40 P.M. | 11 P.M. | Working on creating a terminal Python appliction to get the changes/names/id/files in Drive
Quang Ly | 2018-08-29 | 11:45 P.M. | 1:00 A.M. | Print out all revisions of all files in user's drive in formatted output
Quang Ly | 2018-08-30 | 7:00 P.M. | 11:00 P.M. | Show the last modifying user of revisions as well as only including team drive files in the scope
Quang Ly | 2018-08-31 | 12:00 A.M | 2:00 A.M. | Formats the printing output onto the console
Jack Beard | 2018-08-31 | 4:00 P.M | 7 P.M. | Worked on product and sprint backlogs
Isara Arunanondchai | 2018-08-31 | 4.00 P.M | 7 P.M. | Worked on product and sprint backlogs
Vibhas Kamal | 2018-08-31 | 4.00 P.M | 7 P.M. | Worked on product and sprint backlogs
Vibhas Kamal | 2018-08-31 | 11:37 P.M. | 12:56 A.M. | Made changes to the Product Backlog, Sprint Backlog and updated the Project Inception document to better reflect the team's practices
Quang Ly | 2018-09-01 | 17:30 P.M. | 18:00 P.M. | Consulted the Product Owner and added new user stories into the Product Backlog
Vibhas Kamal | 2018-09-01 | 17:30 P.M. | 18:00 P.M. | Added new user stories into the Product Backlog
Isara Arunanondchai | 2018-09-06 | 12:00 P.M. | 13:00 P.M. | Worked on understanding the listing functionality to retreive changes.
Isara Arunanondchai | 2018-09-06 | 13:00 PM | 14:30 PM | Worked with retrieving changes between each revision within the code. Work in progress.
Quang Ly | 2018-09-06 | 9:00 P.M. | 11:00 P.M. | Refactored the main program by splitting it into multiple functions as well as adding comments
Jack Beard | 2018-09-07 | 5.40 P.M | 6:10 P.M | Created templates for sprint review and retrospective
Quang Ly | 2018-09-07 | 6:00 P.M. | 9:00 P.M. | Work on sprint review and sprint retrospective documents
Isara Arunanondchai | 2018-09-07 | 5:40 P.M. | 7:30 P.M. | Collaborated on sprint review and sprint retrospective.
Manvendra Singh | 2018-09-07 | 4:00 P.M. | 9:00 P.M. | Worked on sprint review and sprint retrospectives
Jack Beard | 2018-09-07 | 6:10 P.M | 7:00 P.M | Added content to both sprint review and sprint retrospective documents
Manvendra Singh | 2018-09-07 | 10:29 P.M. | 11:08 P.M. | Created a user guide for the examiner in the file README.md
Vibhas Kamal | 2018-09-07 | 4:00 P.M. | 9:00 P.M. | Sprint review, discussion regarding the Project Inception, Sprint Retrospective
END OF SPRINT 1
TEAM MEMBER | DATE | START TIME | END TIME | DESCRIPTION OF TASK
Vibhas Kamal | 2018-09-08 | 2:05 A.M. | 3:05 A.M. | Working on creating a server and printing data from python onto a webpage
Vibhas Kamal | 2018-09-10 | 11:20 A.M. | 1:06 P.M. | Created a server, printed data from html file to webpage using that server
Quang Ly | 2018-09-12 | 5:00 P.M | 11:00 | Refactor code, retrieve actions (ie. changes) a user made towards a file
Jack Beard | 2018-09-12 | 7:00 P.M | 9:00 P.M | Initliasing API for plotting, learning functions of the API
Quang Ly | 2018-09-13 | 7:00 P.M. | 11:30 P.M. | Refactor code, categorise changes into the file the change happened
Isara Arunanondchai | 2018-09-13 | 10:30 P.M | 11:30 P.M | Working on understanding how to fix folder within selected drive issue on the API.
Vibhas Kamal | 2018-09-14 | 4:00 P.M | 7:00 P.M | Working on using Python for client side programming and Project Inception
Isara Arunanondchai | 2018-09-14 | 4:00 P.M | 7:00 P.M | Fixed folder issue where program was unable to retrieve files in a folder
Jack Beard | 2018-09-14 | 4:00 P.M | 7:00 P.M | Created working histogram and pie charts that can represent file/team_drive data / revised product backlog & sprint backlog
Quang Ly | 2018-09-14 | 4:00 P.M. | 12:00 A.M. | Refactor code, add new data structures to be passed to graphing modules as parameters and some new additions to the output of the program
Isara Arunanondchai | 2018-09-17 | 4:30 P.M | 5:30 P.M | Changed Definition of Done in Project inception, Updated Sprint Backlog 2
Manvendra Singh | 2018-09-16 | 7:00 P.M | 9:00 P.M | Worked on a piechart function which takes a python dictionary object can be called from a different file (like a flask file) to generate a .png image which can later embedded in html
Manvendra Singh | 2018-09-17 | 8:00 P.M | 9:00P.M | Added functionality to the histogram program like displaying the height of individual bars.
Quang Ly | 2018-09-18 | 8:00 P.M. | 11:00 P.M. | Refactor code, complete data structure File to be passed as parameter for plotting modules
Quang Ly | 2018-09-19 | 3:00 P.M. | 11:00 P.M. | Documentation, calculate contribution for each file
Jack Beard | 2018-09-19 | 11:00 A.M | 12:40 P.M | Met with team to discuss merging code
Vibhas Kamal | 2018-09-19 | 10 A.M. | 10:55 A.M. | Team meeting to discuss the sprint progress
Manvendra Singh | 2018-09-19 | 10A.M | 12:40P.M. | Team meeting to discuss the sprint progress
Isara Arunanondchai | 2018-09-19 | 10 A.M. | 1:20 P.M. | Team meeting to discuss the sprint progress, worked on some code
Quang Ly | 2018-09-19 | 12:00 P.M. | 1:20 P.M. | Team meeting to discuss the sprint progress, worked on some code
Manvendra Singh | 2018-09-19 | 6:00 A.M | 7:00 A.M | Understanding and Implemented the mpld3 package to embed the result in a web page.
Manvendra Singh | 2018-09-19 | 7:00 A.M | 9:00 A.M | Converted the figures and constructs a string of HTML and JavaScript which can be embedded in any webpage.
Quang Ly | 2018-09-20 | 12:00 A.M. | 1:00 A.M. | Discuss product requirements and assess the current state of the sprint backlog
Vibhas Kamal | 2018-09-20 | 12:00 A.M. | 1:00 A.M. | Discuss product requirements and assess the current state of the sprint backlog
Vibhas Kamal | 2018-09-20 | 2:25 P.M. | 3 P.M. | Documentation: Modifying the Project Inception and Sprint Backlog #2
Isara Arunanondchai | 2018-09-20 | 9:00 P.M | 10:15 P.M. | Added functionality that prompts the user if they want to retrieve files from the folder found.
Isara Arunanondchai | 2018-09-21 | 3 P.M. | 3:40 P.M. | Drive summary upon completion of all file retrieval
Quang Ly | 2018-09-21 | 1:00 P.M. | 3:00 P.M. | Change all print functions to now return a string of what was originally to be printed
Manvendra Singh | 2018-09-21 | 4:00 P.M | 7:00 P.M | Team meeting and worked on sprint retrospective
Vibhas Kamal | 2018-09-21 | 4:00 P.M | 8:32 P.M. | Sprint Retrospective, Sprint Review
Quang Ly | 2018-09-21 | 4:00 P.M | 8:32 P.M. | Sprint Retrospective, Sprint Review
Isara Arunanondchai | 2018-09-21 | 4:00 P.M | 8:32 P.M. | Sprint Retrospective, Sprint Review
Jack Beard | 2018-09-21 | 4:00 P.M | 8:32 P.M. | Sprint Retrospective, Sprint Review
END OF SPRINT 2
TEAM MEMBER | DATE | START TIME | END TIME | DESCRIPTION OF TASK
Vibhas Kamal | 2018-09-22 | 4:00 P.M. | 5:30 P.M. | Working on conversion of Python to JS for front-end development
Quang Ly | 2018-09-22 | 5:00 P.M | 9:00 P.M. | Working on conversion of Python to JS using Transcrypt
Vibhas Kamal | 2018-09-23 | 3:53 P.M. | 4:40 P.M. | Created front end template and Transcrypt is now working
Isara Arunanondchai | 2018-09-24 | 4:00 P.M. | 5:00 P.M. | Learning Transcrypt, and applying to our project
Manvendra Singh | 2018-09-24 | 9:00 P.M. | 11:45 P.M. | Added a local function in Piechart to select unique random values and new html test files
Vibhas Kamal | 2018-09-27 | 10:34 A.M. | 11:44 A.M. | Working on conversion of code from Python to JS/HTML using Transcrypt and Brython
Isara Arunanondchai | 2018-09-27 | 10:34 A.M. | 11:44 A.M. | Working on conversion of code from Python to JS/HTML using Transcrypt and Brython
Manvendra Singh | 2018-09-28 | 2:00 P.M. | 6:00 P.M. | Changed look , Stacked the histogram and made it horizontal.
Manvendra Singh | 2018-09-29 | 8:00 A.M | 11:00 A.M | TrIed seaborn api to diplay graphs
Isara Arunanondchai | 2018-09-27 | 7:00 A.M. | 9:00 A.M. | Brython test files
Vibhas Kamal | 2018-09-27 | 12:48 P.M. | 1:20 P.M. | Conversion of Python to JS/HTML
Vibhas Kamal | 2018-09-27 | 2:00 P.M. | 2:24 P.M. | Conversion of Python to JS/HTML
Vibhas Kamal | 2018-09-28 | 11:30 A.M. | 12:40 P.M. | Worked on making python data appear on a webpage using Brython
Vibhas Kamal | 2018-09-28 | 5:40 P.M. | 6:10 P.M. | Made a transcrypt program from scratch
Quang Ly | 2018-10-02 | 7:00 P.M. | 12:00 A.M. | Putting data into big data structure to be passed as big JSON object
Isara Arunanondchai | 2018-10-02 | 11:51 A.M. | 12:51 P.M. | Output being displayed on a server using Flask
Vibhas Kamal | 2018-10-02 | 11:51 A.M. | 12:51 P.M. | Output being displayed on a server using Flask
Jack Beard | 2018-10-02 | 4:00 P.M | 5:00 P.M | Learning basic output to web browsers w/ flask
Manvendra Singh | 2018-10-02 | 11:00 A.M | 12:00 P.M | Reading Flask API
Quang Ly | 2018-10-03 | 1:00 P.M. | 5:00 P.M | Create data structure Drive and fixed technical errors in the calculation of folder's contribution
Manvendra Singh | 2018-10-03 | 9:00 A.M | 11:00 A.M | Trying to work with with flask library to respond to web requests and send HTML
Jack Beard | 2018-10-02 | 6:30 P.M | 10:00 P.M | Taking data structure output from main program and merging it with the graphing programs
Vibhas Kamal | 2018-10-03 | 1:00 A.M. | 3:00 A.M. | Printing data on a webpage by retrieving data from a JS file
Jack Beard | 2018-10-03 | 10:50 A.M | 1:00 P.M | Creating js/HTML pie chart function
Quang Ly | 2018-10-04 | 8:00 P.M. | 12:30 A.M. | Refactor data structure and its method + Getting the data structure onto Flask server
Quang Ly | 2018-10-05 | 4:30 P.M. | 6:00 P.M. | Adding buttons to all the drives and folders and files + Successful sending of data structure to server
Isara Arunanondchai | 2018-10-05 | 5:00 P.M | 6:15 P.M. | Mock test for faster debugging - with David's help
Manvendra Singh | 2018-10-05 | 8:00 P.M | 12:00 A.M | Javascript and html implementation of the horizontal stacked histogram made
Quang Ly | 2018-10-06 | 3:20 P.M. | 3:45 P.M. | Adding buttons to all the drives and folders and files in to target html
Manvendra Singh | 2018-10-06 | 9:00 A.M | 10:30 A.M | Finished making the function create_histogram
Isara Arunanondchai | 2018-10-08 | 12:30 P.M. | 2:00 P.M. | Creating dynamic variables to store values associated with each button
Quang Ly | 2018-10-08 | 5:30 P.M. | 12:00 A.M. | Dealing with POST data + Stops the website from re-calculating data all the time
Jack Beard | 2018-10-08 | 7:00 P.M | 2.00 A.M | Creating programs to create and display pie charts (with appropriate parameters) after having a button clicked
Quang Ly | 2018-10-09 | 12:00 A.M. | 4:00 A.M. | Update the looks of the interface + Add a Back button to navigate back to an upper level (folder -> team drive)
Quang Ly | 2018-10-09 | 6:00 P.M. | 11:00 P.M. | Integrate Jack's file and can now draw pie charts on HTML + calculation contribution for drives
Vibhas Kamal | 2018-10-09 | 10:30 P.M. | 11:20 P.M. | Working on manipulating dictionary data type in Python
Isara Arunanondchai | 2018-10-09 | 5:30 P.M. | 6:30 P.M. | Documentation for mock tests
Manvendra Singh | 2018-10-09 | 9:00 P.M. | 9:45 P.M. | Added documentation in the bar chart html and js files
Quang Ly | 2018-10-10 | 7:00 P.M. | 11:30 P.M. | Integrate Manvendra and Vibhas's file to plot histogram on HTML + calculate histogram data
Vibhas Kamal | 2018-10-10 | 1:00 A.M. | 4:05 A.M. | Changed the codebase for histogram generation to allow it to handle dictionaries as an input
Quang Ly | 2018-10-11 | 7:00 P.M. | 11:00 P.M. | Switching between pie charts and histograms for files/folders/drives
Isara Arunanondchai | 2018-10-12 | 5:45 P.M. | 6:16 P.M. | Product Review
Manvendra Singh | 2018-10-12 | 5:45 P.M. | 6:16 P.M. | Product Review
Jack Beard | 2018-10-12 | 5:45 P.M. | 6:16 P.M. | Product Review
Quang Ly | 2018-10-12 | 5:45 P.M. | 6:16 P.M. | Product Review