## Sheet1
TEAM MEMBER | DATE | START TIME | END TIME | DESCRIPTION OF TASK
Vibhas Kamal | 2018-09-08 | 2:05 A.M. | 3:05 A.M. | Working on creating a server and printing data from python onto a webpage
Vibhas Kamal | 2018-09-10 | 11:20 A.M. | 1:06 P.M. | Created a server, printed data from html file to webpage using that server
Quang Ly | 2018-09-12 | 5:00 P.M | 11:00 P.M. | Refactor code, retrieve actions (ie. changes) a user made towards a file
Jack Beard | 2018-09-12 | 7:00 P.M | 9:00 P.M | Initliasing API for plotting, learning functions of the API
Quang Ly | 2018-09-13 | 7:00 P.M. | 11:30 P.M. | Refactor code, categorise changes into the file the change happened
Isara Arunanondchai | 2018-09-13 | 10:30 P.M | 11:30 P.M | Working on understanding how to fix folder within selected drive issue on the API.
Vibhas Kamal | 2018-09-14 | 4:00 P.M | 7:00 P.M | Working on using Python for client side programming and Project Inception
Isara Arunanondchai | 2018-09-14 | 4:00 P.M | 7:00 P.M | Fixed folder issue where program was unable to retrieve files in a folder
Jack Beard | 2018-09-14 | 4:00 P.M | 7:00 P.M | Created working histogram and pie charts that can represent file/team_drive data / revised product backlog & sprint backlog
Quang Ly | 2018-09-14 | 4:00 P.M. | 12:00 A.M. | Refactor code, add new data structures to be passed to graphing modules as parameters and some new additions to the output of the program
Isara Arunanondchai | 2018-09-17 | 4:30 P.M | 5:30 P.M | Changed Definition of Done in Project inception, Updated Sprint Backlog 2
Manvendra Singh | 2018-09-16 | 7:00 P.M | 9:00 P.M | Worked on a piechart function which takes a python dictionary object can be called from a different file (like a flask file) to generate a .png image which can later embedded in html
Manvendra Singh | 2018-09-17 | 8:00 P.M | 9:00P.M | Added functionality to the histogram program like displaying the height of individual bars.
Quang Ly | 2018-09-18 | 8:00 P.M. | 11:00 P.M. | Refactor code, complete data structure File to be passed as parameter for plotting modules
Quang Ly | 2018-09-19 | 3:00 P.M. | 11:00 P.M. | Documentation, calculate contribution for each file
Jack Beard | 2018-09-19 | 11:00 A.M | 12:40 P.M | Met with team to discuss merging code
Vibhas Kamal | 2018-09-19 | 10 A.M. | 10:55 A.M. | Team meeting to discuss the sprint progress
Manvendra Singh | 2018-09-19 | 10A.M | 12:40P.M. | Team meeting to discuss the sprint progress
Isara Arunanondchai | 2018-09-19 | 10 A.M. | 1:20 P.M. | Team meeting to discuss the sprint progress, worked on some code
Quang Ly | 2018-09-19 | 12:00 P.M. | 1:20 P.M. | Team meeting to discuss the sprint progress, worked on some code
Manvendra Singh | 2018-09-19 | 6:00 A.M | 7:00 A.M | Understanding and Implemented the mpld3 package to embed the result in a web page.
Manvendra Singh | 2018-09-19 | 7:00 A.M | 9:00 A.M | Converted the figures and constructs a string of HTML and JavaScript which can be embedded in any webpage.
Quang Ly | 2018-09-20 | 12:00 A.M. | 1:00 A.M. | Discuss product requirements and assess the current state of the sprint backlog
Vibhas Kamal | 2018-09-20 | 12:00 A.M. | 1:00 A.M. | Discuss product requirements and assess the current state of the sprint backlog
Vibhas Kamal | 2018-09-20 | 2:25 P.M. | 3 P.M. | Documentation: Modifying the Project Inception and Sprint Backlog #2
Isara Arunanondchai | 2018-09-20 | 9:00 P.M | 10:15 P.M. | Added functionality that prompts the user if they want to retrieve files from the folder found.
Isara Arunanondchai | 2018-09-21 | 3 P.M. | 3:40 P.M. | Drive summary upon completion of all file retrieval
Quang Ly | 2018-09-21 | 1:00 P.M. | 3:00 P.M. | Change all print functions to now return a string of what was originally to be printed
Manvendra Singh | 2018-09-21 | 4:00 P.M | 7:00 P.M | Team meeting and worked on sprint retrospective
Vibhas Kamal | 2018-09-21 | 4:00 P.M | 9:00 P.M. | Sprint Retrospective, Sprint Review, put things inside the folder to be pushed to main branch
Quang Ly | 2018-09-21 | 4:00 P.M | 9:00 P.M. | Sprint Retrospective, Sprint Review, put things inside the folder to be pushed to main branch
Isara Arunanondchai | 2018-09-21 | 4:00 P.M | 9:00 P.M. | Sprint Retrospective, Sprint Review, put things inside the folder to be pushed to main branch
Jack Beard | 2018-09-21 | 4:00 P.M | 9:00 P.M. | Sprint Retrospective, Sprint Review, put things inside the folder to be pushed to main branch